## Sheet1
Carpio, John Jazpher DC.
Developer
ACTIVITIES | February |  |  |  | March |  |  |  | April |  |  |  | May
| 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th | 1st | 2nd | 3rd | 4th
1. Conceptualizing, Brainstorming, and Formulating capstone project title | bar: February 1st to February 2nd
2. Meeting with the project team
3. Creating a prototype of the system | bar: February 3rd to February 4th
4. Coding the system | bar: March 1st to April 2nd
5. Checking the quality of the system | bar: April 3rd
6. Fixing bugs in the system | bar: April 4th to May 2nd
7. Preparation for final defense | bar: May 3rd to May 4th